|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Project Status Report** | Project | | | MedicOnDemand |
| Reporting Period | | | 4th March to 8th March |
| **Overall Project Summary** | | | |  |
| **Project status remains at YELLOW:** Potential issues with schedule, but can be solved with corrective actions.  **Overview:**   * Requirements to implement medication adherences have been discussed. * Integrating push notifications in the iOS application is in progress and back-end support to attain the functionality is in progress to provide support for various notifications. * iOS application for Indian locality has been released to test flight. * Payment gateway integration for Indian locality needs to be discussed. * After discussing about integrating Google Maps API for location services, we decided not to use it, but to store the cities, states and zip/pin codes in our database. * Changes to upload bulk users on the administrator end to support the multi-tenant architecture and the login logic for these users have been completed. | | | | |
| **KEY ACTIVITIES COMPLETED THIS WEEK** | | | | |
| **Functional:**   * Issues/changes related to Indian locality have been completed. * Sending a push notification on iOS application upon initiating a tele-health conference is completed. * Uploading bulk users and attaching those users to relevant clients/tenants on the administrator end is completed. * Changes in login logic for the users uploaded by the administrator have been implemented.   **Testing:**   * Rigorous testing on video conference on both clinic and regular workflows – Connections are established as expected with users coming in from both web and iOS applications. * Testing on push notifications to the doctor when a tele-health conference is initiated – testing is in progress and issues are reported to the developers. * Testing the administrator module to upload bulk users – testing is progress and issues are reported to the developers. * Testing on registration and login modules after redesigning them into the multi-tenant architecture are yielding expected results. | | | | |
| **Activities In Progress** | | **Next Action** | **Due Date** | |
| Push notifications on iOS Application across various modules. | | Development | TBD | |
| Bulk users upload on the administrator end | | Testing | 03/12/2019 | |
| Login conditions for users uploaded by the administrator | | Testing | 03/13/2019 | |
| **KEY ACTIVITIES TO BE STARTED NEXT WEEK** | | | | |
| * Medical Adherences: Send timed notifications to patients about medications to be taken. | | | | |
| **CONCLUSIONS AND RECOMMENDATIONS** | | | | |
| * All changes related to bulk user upload are completed and deployed to the Dev instance and testing is in progress. * We need to decide upon the gateway to be used for payment in Indian locality. | | | | |