## MOD_devIssues
Sl No | Role | Workflow | Module | Issues | Reported On | Priority | Informed To | Fixed By | Fixed On/ Refixed On | Issue Staus | Tested/ Retested On | Test Results Pass/Fail | Comments
dev.medicondemand.com
Tele-health Issues
1 | Both | Both | Tele health: Info | Health history fields not loading |  | High | Bharath |  |  | Open
2 | Both | Both | Tele health: Info | Health history: Modal is not getting closed when clicking on "OK" |  | High | Bharath |  |  | Open
3 | Both | Both | Tele health: Info | Health history: can see different timings for added documents from doctor and patient side, though they both are from same time zone |  | High | Bharath |  |  | Open
4 | Both | Both | Tele health: Info | Health history: Getting health condition with document added in the the modal though patient hasn't added any health history in the profile |  | High | Bharath |  |  | Open
5 | Patient | Both | Tele health: Waiting room | When patient clicked on cancel request and clicked on Yes again to confirm, got message “Operation Not allowed”: Intermittent |  | High | Yashwanth | Bharath |  | Fixed |  | Pass
6 | Doctor | Both | Tele health: Waiting room | Doctor got Access denied: When a patient is sending a connection request the countdown should start immediately. If doctor accepts the request before countdown starts, doctor is getting “Access denied” |  | High | Yashwanth | Bharath |  | Reopened |  | Fail | Intermittent
7 | Both | Both | Tele health:Info | Unable to see the uploaded health history documents from moderator and doctor side on Web |  | High | Bharath | Bharath |  | Fixed |  | Pass
8 | Both | Clinic | Tele health:Info | Health history: reported at time is different for both doc and patient in health conditions and family health history |  | High | Bharath | Bharath |  | Open
9 | Doctor | Both | Tele health: Consultation | Doctor invited as a 2nd doctor is not available in the doctor’s list if it is not accepting the invitation within two mins |  | Medium | Yashwanth |  |  | Open
10 | Both | Both | Tele health: Chat | getting auto suggestions also need to scroll down to see new chats |  | High | Bharath | Bharath |  | Fixed |  | Pass
11 | Both | Retail | Tele health: Documents | When patient uploads a document in the 2nd step of connecting a doctor, document field on left panel of tele health becoming inactive and we are unable to see visit page after disconnected from tele health |  | High | Bharath | Bharath |  | Reopened |  | Fail
12 | Both | Both | Tele health: Notes | After adding ICD10 codes, Text box is not getting resetted |  | Low | Bharath | Bharath |  | Reopened |  | Fail | Text box is not getting resetted immediately after adding
Other Module Issues
Admin
1 | Admin | Both | Bulk Upload | Unable to Upload patients csv file: dev1 | 2019-03-12 | High | Yashwanth |  |  | Fixed | 2019-03-13 | Pass
2 | Admin | Both | Bulk Upload | Unable to Upload doctors csv file : dev1 | 2019-03-12 | High | Yashwanth |  |  | Fixed | 2019-03-13 | Pass
3 | Admin | Both | Bulk Upload | Unable to see uploaded patients from moderator side: dev1 | 2019-03-13 | High | Yashwanth |  |  | Fixed | 2019-03-13 | Pass
4 | Admin | Both | Bulk Upload | Unable to validate doctors from local Admin: dev1 | 2019-03-13 | High | Yashwanth |  |  | Open
5 | Admin |  | Bulk Upload | Address, City, State, Zip added to csv files are not uploading for doctor/patient on app | 2019-03-13 | High | Yashwanth |  |  | Open
6 | Admin | Both | Bulk Upload | Change Password's don't match to Passwords don't match | 2019-03-13 | High | Yashwanth |  |  | Open
7 | Admin | Both | Bulk Upload | Patient: Add visit: !Please enter all required fields to contact a doctor => shift the exclamation right | 2019-03-14 | Medium | Yashwanth |  |  | Open
8 | Admin | Both | Bulk Upload | Patient: After changing pwd, patient should redirected to Dashboard | 2019-03-14 | High | Yashwanth |  |  | Open
| Admin | Both | Bulk Upload | Patient: After login, getting message "You must activate account to get full access" | 2019-03-14 | High | Yashwanth |  |  | Open
9 | Admin | Both | Bulk Upload | Unable to Upload patients csv file, getting internal server error: dev2 | 2019-03-14 | High | Yashwanth |  |  | Open
10 | Admin | Both |  | Appointment ID is missing in patient visit info |  |  | Yashwanth |  |  | Open
11 | Admin | Both |  | Can see Offline doctors as Online from Admin side |  |  | Yashwanth |  |  | Open
Moderator
1 | Moderator | Both |  | Once the doctors disconnected the call, unable to see them in the dropdown list: Intermittent |  |  | Yashwanth |  |  | Open
2 | Moderator | Both | Registration | Able to save a phone number of less than 10 digits |  |  | Yashwanth | Bharath |  | Fixed |  | Pass
Patient & Doctor
1 | Both | Both | All | All the mandatory fields should be marked with asterisks(*) |  |  | Yashwanth | Bharath |  | Fixed |  | Pass | .
2 | Patient | Retail | Contact a Doctor now | Patient sends a request to doctor and doc didn't accept, at 5 mins, patient gets a pop-up asking to reschedule the appointment. Clicking "No" navigates to Upcoming visits page |  |  | Yashwanth |  |  | Open
3 | Patient | Retail | Contact a Doctor now | Scheduled Visits: getting slots only as per IST, and the countdown for slots booked for timings in pm are coming first than am under Upcoming visits |  | High | Bharath |  |  | Open
4 | Doctor | Retail | Notifications | When doctor gets multiple Ondemand requests and connect to one patient for Tele health, other patients should get the pop-up "Doctor is not accessible anymore! Would you like to reschedule?" instantly |  | High | Bharath |  |  | Open
5 | Patient | Retail | Health history/Patient health locker | Share with your care provider: Not able to select a doctor to share medical condition |  |  | Yashwanth | Bharath |  | Fixed
6 | Patient | Clinic | Profile | Unable to Save DOB |  | High | Bharath | Bharath |  | Reopened |  | Fail
7 | Doctor | Clinic | Profile | Unable to update contact number |  | High | Yashwanth |  |  | Reopened |  | Fail
8 | Patient | Clinic | Profile | BMI is not showing up once we go to some other tab and come back |  |  | Bharath | Bharath |  | Reopened |  | Fail | BMI is not showing up once we go to lifestyle and come back
9 | Patient | Clinic | Health history | Share with your care provider: Need to remove this field |  |  | Yashwanth | Yashwanth |  | Fixed
10 | Patient | Retail | Health history/Patient health locker | While adding health history and save the data can see an empty left side and up bar: Intermittent |  | High | Bharath | Bharath |  | Reopened |  | Fail
11 | Patient | Retail | Visit | Can see an empty left side and up bar after tele health: Intermittent |  | High | Bharath |  |  | Open
12 | Doctor | Retail | Notifications=>Calender | The doctor is able to drag the booked slots highlighted on the calender page |  |  | Yashwanth |  |  | Open
13 | Patient | Both | Health history/Patient health locker | Pagination for surgeries not working |  |  | Bharath | Bharath |  | Fixed |  | Pass
14 | Patient | Both | Health history/Patient health locker | Getting different dates for different fields (Family history is showing in PST and others in CST) |  |  | Bharath | Bharath |  | Fixed |  | Pass
15 | Patient | Both | Health history/Patient health locker | Surgeries: Year is not getting resetted |  |  | Bharath | Bharath |  | Fixed |  | Pass
16 | Patient | Retail | Connect to the doctor 3rd step | Not able to filter doctors by City |  | High | Bharath | Bharath |  | Fixed |  | Pass
17 | Both | Retail | Tele health: Info | Info is not working for both Doctor and patient when vitals are added |  | High | Bharath | Bharath |  | Fixed |  | Pass
18 | Patient | Both | Tele health: Chat | Not getting patient’s name in chat window from patient side |  | Medium | Bharath | Bharath |  | Fixed |  | Pass
19 | Both | Both | Tele health: Info | Doctor on web unable to see health history documents uploaded by patient |  | High | Bharath | Bharath |  | Fixed |  | Pass
20 | Moderator | Clinic | Appointments | No options to see whether doctor is free or busy |  |  | Yashwanth |  |  | Open
21 | Moderator | Clinic | Appointments | Able to see the invalidated doctors in the dropdown from moderator side |  |  | Yashwanth | Bharath |  | Fixed |  | Pass
22 | Patient | Clinic | Visits page | "Add Review" button is missing |  |  | Bharath | Bharath |  | Fixed |  | Pass
23 | Moderator | Clinic | Visits page | Need to Remove When did you start feeling this way from clinic workflow visit page |  |  | Bharath | Bharath |  | Reopened |  | Fail
24 | Moderator | Clinic | Tele health: Info | Need to Remove When did you start feeling this way, Second Complaint from clinic workflow visit page |  |  | Bharath | Bharath |  | Reopened |  | Fail
25 | Doctor | Retail | Appointment | Clinic appointment tab should be removed from appointments dropdown |  |  | Bharath |  |  | Open
26 | Doctor | Retail | Appointment: History | Latest appointments should be listed first |  |  | Bharath |  |  | Open
27 | Doctor | Retail | Appointment: History | Appointment ID is missing |  |  | Bharath |  |  | Open
28 | Doctor | Retail | Appointment: History | Page Numbering: Forword and Previous icons are in question mark |  |  | Bharath |  |  | Open
29 | Doctor | Retail | Appointment: History | Table (1st doc n 2nd doc) should be differentiated with names |  |  | Bharath |  |  | Open
30 | Doctor | Retail | Dashboard | Broken profile avatar on dashboard and top menu bar and also doctor's name is missing on dashboard after navigating from other pages |  |  | Bharath |  |  | Open
31 | Moderator | Clinic | Appointment | When patient updates name in profile page, its not getting reflected on appointment page for subsequent appointments |  |  | Bharath |  |  | Open
32 | Patient | Retail | Appointment | Getting Finished visits data under Upcoming visits tab: Intermittent |  |  | Bharath |  |  | Open
33 | Patient | Retail | Notifications: view | Patient is able to add visit Review before Tele health |  |  | Bharath |  |  | Open
34 | Patient | Retail | Visit | Patient Review should be removed from Cancelled visit/Missed visit/ Upcoming visit |  | Low | Bharath | Bharath |  | Fixed |  | Pass
35 | Patient | Retail | Visit | Please add Patient Review button on Finished visit page |  | High | Bharath
36 | Patient | Retail | Visit | “Visit will start in” column should be removed |  | Low | Bharath |  |  | Open
37 | Patient | Retail | Patient Health Locker | The timings for adding the profile are different in Medical records, Labs, Immunization |  |  | Bharath |  |  | Open
38 | Patient | Retail | Documents | Unable to upload, getting internal server error |  | High | Bharath |  |  | Fixed |  | Pass
39 | Patient | Retail | Smart Triage | Can see a broken Logo for smart triage after Tele health |  |  | Bharath |  |  | Open
40 | Patient | Both | Notification and Visit page | Patient image display under Notification and Visit page |  | High | Bharath | Bharath |  | Fixed |  | Pass
41 | Patient | Clinic | Profile | Unable to upload patient profile image on Clinic workflow |  | High | Bharath | Bharath |  | Fixed |  | Pass
42 | Doctor | Retail | General schedule | Unable to save calendar, keeps loading…. |  | High | Yashwanth | Yashwanth |  | Fixed |  | Pass
43 | Both | Both | Tables | Recently added should shown on top of the table |  |  | Bharath | Bharath |  | Fixed
44 | Patient | Both | Waiting room | !Doctor is not accessible anymore: shift the exclamation to right |  |  | Bharath | Bharath |  | Fixed
45 | Patient | Both | Tele health: Chat | During three way calling, patient is unable to differentiate the chats sending by both the doctors |  |  | Yashwanth |  |  | Open
46 | Patient | Both | Appointments: My Visits | Remove "Visit will start in" column for Finished/missed/cancelled visits | 2019-03-13 |  | Bharath |  |  | Open
47
48
49
50
51
52

## MOD_sjmedicalIssues
Sl No | Role | Workflow | Module | Issues | Reported on | Priority | Informed To | Fixed By | Issue Staus | Test Results Pass/Fail | Comments
sjmedical.medicondemand.com
1 | Admin | Both |  | Appointment ID is missing in patient visit info |  |  | Yashwanth |  | Open
2 | Admin | Both |  | Can see Offline doctors as Online from Admin side |  |  | Yashwanth |  | Open
3 | Moderator | Both |  | Once the doctors disconnected the call, unable to see them in the dropdown list: Intermittent |  |  | Yashwanth |  | Open
4 | Moderator | Both |  | Able to save a phone number of less than 10 digits |  |  | Yashwanth | Bharath | Fixed
5 |  |  |  | All the mandatory fields should be marked with asterisks(*) |  |  | Yashwanth | Bharath | Fixed
6 | Patient | Retail | Contact a Doctor now | Patient sends a request to doctor and doc didn't accept, at 5 mins, patient gets a pop-up asking to reschedule the appointment. Clicking "No" navigates to Upcoming visits page |  |  | Yashwanth |  | Open
7 | Patient | Retail | Contact a Doctor now | Scheduled Visits: getting slots only as per IST, and the countdown for slots booked for timings in pm are coming first than am under Upcoming visits |  | High | Bharath |  | Open
8 | Patient | Retail | Health history/Patient health locker | Share with your care provider: Not able to select a doctor to share medical condition |  |  | Yashwanth |  | Open
9 | Patient | Clinic | Profile | Unable to Save DOB |  | High | Bharath | Bharath | Fixed | Pass
10 | Doctor | Clinic | Profile | Unable to update contact number |  | High | Yashwanth |  | Open
11 | Patient | Both | Profile | BMI is not showing up once we go to some other tab and come back |  |  | Bharath | Bharath | Fixed | Pass
12 | Patient | Clinic | Profile | BMI is not showing up once we go to lifestyle and come back |  |  | Bharath |  | Open
13 | Patient | Clinic | Health history | Share with your care provider: Need to remove this field |  |  | Yashwanth | Yashwanth | Reopened
14
15 | Patient | Retail | Health history/Patient health locker | While adding health history and save the data can see an empty left side and up bar: Intermittent |  | High | Bharath | Bharath | Reopened
16 | Doctor | Retail | Notifications=>Calender | The doctor is able to drag the booked slots highlighted on the calender page |  |  | Yashwanth |  | Open
17 | Patient | Both | Health history/Patient health locker | Pagination for surgeries not working |  |  | Bharath | Bharath | Fixed | Pass
18 | Patient | Both | Health history/Patient health locker | Getting different dates for different fields (Family history is showing in PST and others in CST) |  |  | Bharath | Bharath | Fixed
19 | Patient | Both | Health history/Patient health locker | Surgeries: Year is not getting resetted |  |  | Bharath | Bharath | Fixed | Pass
20 | Patient | Retail | Connect to the doctor 3rd step | Not able to filter doctors by City |  | High | Bharath | Bharath | Fixed | Pass
21 | Patient | Both | Tele health: Waiting room | When patient clicked on cancel request and clicked on Yes again to confirm, got message “Operation Not allowed”: Intermittent |  |  | Yashwanth | Bharath | Fixed
22 | Doctor | Both | Tele health: Waiting room | Doctor got Access denied: When a patient is sending a connection request the countdown should start immediately. If doctor accepts the request before countdown starts, doctor is getting “Access denied” |  | High | Yashwanth | Bharath | Reopened | Fail
23 | Both | Both | Tele health:Info | Unable to see the uploaded health history documents from moderator and doctor side on Web |  | High | Bharath | Bharath | Fixed | Pass
24 | Doctor | Both | Tele health: Consultation | Doctor invited as a 2nd doctor is not available in the doctor’s list if it is not accepting the invitation within two mins |  |  | Yashwanth |  | Open
25 | Both | Both | Tele health: Chat | getting auto suggestions also need to scroll down to see new chats |  | High | Bharath | Bharath | Reopened | Fail
26 | Moderator | Clinic | Appointments | No options to see whether doctor is free or busy |  |  | Yashwanth |  | Open
27 | Both | Retail | Tele health: Documents | When patient uploads a document in the 2nd step of connecting a doctor, document field on left panel of tele health becoming inactive and we are unable to see visit page after disconnected from tele health |  |  | Bharath | Bharath | Reopened | Fail
28 | Both | Both | Tele health: Notes | After adding ICD10 codes, Text box is not getting resetted |  |  | Bharath | Bharath | Reopened | Fail
29 | Moderator | Clinic | Appointments | Able to see the invalidated doctors in the dropdown from moderator side |  |  | Yashwanth | Bharath | Fixed
30 | Patient | Clinic | Visits page | "Add Review" button is missing |  |  | Bharath | Bharath | Fixed | Pass
31 | Moderator | Clinic | Visits page | Need to Remove When did you start feeling this way from clinic workflow visit page |  |  | Bharath | Bharath | Fixed | Fail
32 | Moderator | Clinic | Tele health: Info | Need to Remove When did you start feeling this way, Second Complaint from clinic workflow visit page |  |  | Bharath | Bharath | Fixed | Fail
33 | Doctor | Retail | Appointment | Clinic appointment tab should be removed from appointments dropdown |  |  | Bharath |  | Open
34 | Doctor | Retail | Appointment: History | Latest appointments should be listed first |  |  | Bharath |  | Open
35 | Doctor | Retail | Appointment: History | Appointment ID is missing |  |  | Bharath |  | Open
36 | Doctor | Retail | Appointment: History | Page Numbering: Forword and Previous icons are in question mark |  |  | Bharath |  | Open
37 | Doctor | Retail | Appointment: History | Table should be differentiated with names |  |  | Bharath |  | Open
38 | Doctor | Retail | Dashboard | Broken profile avatar on dashboard and top menu bar and also doctor's name is missing on dashboard after navigating from other pages |  |  | Bharath |  | Open
39 | Moderator | Clinic | Appointment | When patient updates name in profile page, its not getting reflected on appointment page for subsequent appointments |  |  | Bharath |  | Open
40 | Patient | Retail | Appointment | Getting Finished visits data under Upcoming visits tab: Intermittent |  |  | Bharath |  | Open
41 | Patient | Retail | Notifications: view | Patient is able to add visit Review before Tele health |  |  | Bharath |  | Open
42 | Patient | Retail | Visit | Cancelled visit/Missed visit: Patient is able to add visit Review |  |  | Bharath |  | Open
43 | Patient | Retail | Visit | “Visit will start in” column should be removed |  |  | Bharath |  | Open
44 | Patient | Retail | Patient Health Locker | The timings for adding the profile are different in Medical records, Labs, Immunization |  |  | Bharath |  | Open
45 | Patient | Retail | Documents | Unable to upload, getting internal server error |  |  | Bharath |  | Open
46 | Patient | Retail | Smart Triage | Can see a broken Logo for smart triage after Tele health |  |  | Bharath |  | Open
47 | Both | Both | Tele health: Info | jpg, png and pdf documents which opens in a new tab, url shows test.medicondemand.com |  | High | Bharath |  | Open
48 | Patient | Both | Notification and Visit page | Patient image display under Notification and Visit page |  | High | Bharath | Bharath | Fixed | Pass
49 | Patient | Both | Tele health: Chat | Not getting patient’s name in chat window from patient side |  | Medium | Bharath | Bharath | Fixed | Pass
50 | Both | Both | Tele health: Info | Doctor on web unable to see health history documents uploaded by patient |  | High | Bharath | Bharath | Fixed | Pass
51 | Patient | Clinic | Profile | Unable to upload patient profile image on Clinic workflow |  | High | Bharath | Bharath | Fixed | Pass
52 | Both | Retail | Tele health: Info | Info is not working for both Doctor and patient when vitals are added |  | High | Bharath | Bharath | Fixed | Pass
53 | Doctor | Retail | General schedule | Unable to save calendar, keeps loading…. |  | High | Yashwanth | Yashwanth | Fixed | Pass
54 | Patient | Both | Profile | Need asterisks for mendatory fields under Contact |  |  | Bharath |  | Open

## MOD_inIssues
Sl No | Role | Workflow | Module | Issues | Reported On | Priority | Informed To | Fixed By | Fixed/ refixed On On | Issue Staus | Test Results Pass/Fail | Tested/ Retested On | Comments
in.medicondemand.com
1 | Patient | Retail | Profile | Date Format: Change from USA to India |  |  | Bharath | Bharath |  | Fixed | Pass
2 | Patient | Retail | Profile | DOB change the date format: DD/MM//YYYY |  |  | Bharath | Bharath |  | Fixed | Pass
3 | Doctor | Retail | Profile | DOB, States licensed in: Expiry,change the date format: DD/MM//YYYY |  |  | Bharath | Bharath |  | Fixed | Pass
4 | Patient | Retail | Profile | Unable to see Primary physician field after saving the profile |  |  | Bharath | Bharath |  | Fixed | Pass
5 | Patient | Retail | Profile | Profile meter is not showing 100% when all the fields are filled and saved |  |  | Bharath | Bharath |  | Fixed | Pass
6 | Patient | Retail | Profile | DOB is not getting saved |  |  | Bharath | Bharath |  | Fixed | Pass
7 | Doctor | Retail | Notifications | Patients in queue/Upcoming visits: Date format is YYYY/MM/DD |  |  | Bharath |  |  | Not a bug
8 | Patient | Both | Profile | Registered mobile number is not showing when logged in as new patient |  |  | Bharath | Bharath |  | Fixed | Pass
9 | Patient | Both | Health history | Unable to add Family History and Health Conditions |  |  | Bharath | Bharath |  | Fixed | Pass
10 | Patient | Retail | Contact a Doctor | If 2 or more files are added before connecting the call in telehealth Documents modal is unable to open and after disconnecting the call visit page is not showing up |  |  | Bharath |  |  | Open
11 | Both | Both | Telehealth:Chat | Not scrolling down automatically |  |  | Bharath | Bharath |  | Fixed | Pass
12 | Both | Retail | Telehealth:Info- | Scheduled appointment: Info is not working |  |  | Bharath | Bharath |  | Fixed | Pass
13 | Both | Retail | Telehealth: Documents | In documents uploaded document Uploaded at format if different (YYYY/MM/DD: hh:mm:ss) |  |  | Bharath | Bharath |  | Fixed | Pass
14 | Patient | Retail | Patient health locker | Share with your care provider: Unable to search doctors by firstname/Last name (Except Medications) |  |  | Bharath | Bharath |  | Reopened | Fail
15 | Both | Retail | My visist | Getting duplicate Appointment IDs for all Missed/Cancelled/Finished visits |  |  | Bharath
16 | Doctor | Retail | Calendar | General schedule details are reflecting in Calendar: Intermittent |  |  | Bharath | [5 empty] | Unable to reproduce
17 | Doctor | Retail | Calendar | Date format: Start & End are in US format (MM/DD/YYYY) |  |  | Bharath | Bharath |  | Fixed | Pass
18 | Doctor | Retail | Notifications | Upcoming visits Date format (YYYY/MM/DD : hh:mm:ss) |  |  | Bharath | Bharath |  | Fixed | Pass
19 | Moderator | Clinic | Appointments | When call is cancelled from moderator side, can see waiting room in left side bar |  |  | Bharath | Bharath |  | Fixed | Pass
20 | Moderator | Clinic | Telehealth | In documents uploaded document Uploaded at format (YYYY/MM/DD: hh:mm:ss) |  |  | Bharath | Bharath |  | Fixed | Pass
21 | Moderator | Clinic | Profile | BMI value is not showing when clicks another page and came back |  |  | Bharath | Bharath |  | Fixed | Pass
22 | Both | Both | Profile | Pin code text box: Select ZIP should be select PIN |  |  | Bharath | Bharath |  | Fixed | Pass
23 | Both | Both | Telehealth | Info: Font style for numbers |  |  | Bharath | Bharath |  | Fixed | Pass
24 | Patient | Both | Profile | Home phone number: Add landline Indian number format |  |  | Bharath | Bharath |  | Reopened | Fail |  | Not fixed for Clinic Workflow
25 | Doctor | Both | Telehealth | Getting Access Denied when Doctor connects the call: Intermittent |  |  | Bharath | Bharath |  | Open
26 | Both | Retail | Left panel | When we scroll, entire left panel is scrolling down, should be fixed instead | [5 empty] | Open
27 | Patient | Both | Profile | Change lbs to kgs |  |  | Bharath | Bharath |  | Fixed | Pass
28 | Both | Both | Tables | Recently added should shown on top of the visits page |  |  | Bharath | Bharath | 2019-03-12 | Fixed | Pass | 2019-03-13
29 | Patient | Both | Waiting room | !Doctor is not accessible anymore: shift the exclamation to right |  |  | Bharath | Bharath | 2019-03-12 | Fixed | Pass | 2019-03-13
30 | Patient | Both | Telehealth: Info | added vitals are not getting displayed when doc is on iOS and patient on Web |  |  | Bharath |  |  | Open
31 | Both | Retail | Telehealth: Info | change lbs to kgs |  |  | Bharath | Bharath |  | Fixed | Pass
32 | Both | Retail | Visit page | patient Info: change lbs to kgs |  |  | Bharath | Bharath |  | Fixed | Pass
33 | Patient | Retail | Family member | change lbs to kgs |  |  | Bharath | Bharath |  | Fixed | Pass
34 | Both | Retail | Tele health: Chat | During three way calling, patient is unable to differentiate the chats sending by both the doctors |  |  | Yashwanth |  |  | Open
35 | Doctor | Retail | Appointments | Left side menu: Appointments: Remove Clinic appointments |  |  | Bharath | Bharath | 2019-03-12 | Fixed | Pass | 2019-03-13
36 | Patient | Both | Profile | Need asterisks for mendatory fields under Contact |  |  | Bharath |  |  | Open
37 | Patient | Both | Appointments: My Visits | Remove "Visit will start in" column for Finished/missed/cancelled visits | 2019-03-13 |  | Bharath |  |  | Open
38 | Both | Both | Appointments: My Visits | visit date mentioned twice | 2019-03-14 |  | Bharath |  |  | Open
39 | Both | Both | Appointments: My Visits | Names are coming in encrypted format when open the page for the first time, works fine after refreshing | 2019-03-14 |  | Bharath |  |  | Open
40 | Moderator | Clinic | Waiting room | !Sorry the doctor cancelled the visit => shift the exclamation to the right of sorry | 2019-03-14 |  | Bharath |  |  | Open